## Sheet1
ReqID | Category | User | Requirement | Dependencies | Priority | TimeEstimate (Days)
1 | Must | Admin | The admin must be able to login to the system. | NA | 10 | 3
2 | Must | Admin | The admin must be able to post polls for the citizens to view. | 1 | 10 | 3
3 | Must | Citizen | The citizen must be able to login to the system. | NA | 10 | 3
4 | Must | Citizen | The citizen must be able to provide feedback to municipality via web form. | NA | 10 | 2
5 | Must | System | The system must be AODA/WCAG/PIPEDA compliant. | NA | 10 | 2
6 | Must | System | The system must be fully functional on all web browsers. | NA | 10 | 3
7 | Must | System | The system must provide information to citizen regarding privacy and data collection. | NA | 20 | 1
8 | Must | Citizen | The citizen must be required to login to create posts. | 3 | 10 | 3
9 | Must | Citizen | The citizen must be able to post events they're hosting. | 2022-08-03 | 10 | 2
10 | Must | Admin | The admin must be able to post events they're hosting. | 1 | 10 | 2
11 | Must | Admin | The admin must be able to view all events posted by citizens. | 1 | 10 | 2
12 | Must | Admin | The admin must be able to view citizen poll results. | 2022-02-01 | 10 | 2
13 | Must | Citizen | The citizen must be able to upvote events they're interested in. | 9 | 20 | 2
14 | Must | Citizen | The citizen must be able to see the popularity of city events. | 2013-10-09 | 20 | 3
15 | Must | Citizen | The citizen must be able to view all polls available to vote in. | 2 | 10 | 2
16 | Must | System | The system must be fully responsive on all devices. | NA | 10 | 2
17 | Must | Admin | The admin must be required to login after 30 minutes of inactivity. | 1 | 10 | 4
18 | Must | Admin | The admin must have a dashboard to visualize data. | 1 | 10 | 4
19 | Must | Admin | The admin must be able to change their login information. | 1 | 10 | 2
20 | Must | System | The system must have an option to change site font sizes. | 5 | 20 | 2
21 | Must | System | The system allows flexible data input. | 1 | 20 | 4
22 | Must | Citizen | The citizen must be able to comment on event postings. | 2022-02-09 | 20 | 2
23 | Must | System | The system must connect to disqus API for citizens to add public comments to events. | 22 | 20 | 4
24 | Must | Citizen | The citizen must be able to flag inappropriate comments. | 22 | 20 | 2
25 | Must | System | The system must provide updates and news to the main page to offer public insight to municipal progress. | 2002-10-09 | 10 | 3
26 | Must | Citizen | The citizen must be able to see the vote counts for polls. | 2 | 10 | 1
27 | Must | System | The system must have a maintenance mode in case an important functionality is broken. | NA | 10 | 4
28 | Must | System | The system must ensure that no third parties have access to our internal information. | NA | 10 | 3
29 | Must | System | The system must support the ability to easily run analytics to make sure everything is running properly on the site. | NA | 10 | 3
30 | Must | Admin | The admin must be able to gather information on citizen demographics. | 7 | 20 | 1
31 | Must | Admin | The admin must be able to download statistical information about the citizens preferences and opinions. | 1 30 | 20 | 4
32 | Should | Admin | The admin should be able to delete inapprorate citizen posts. | 1 11 | 20 | 1
33 | Should | Citizen | The citizen should be able to delete their own comments off of event postings. | 22 | 20 | 2
34 | Should | Citizen | The citizen should be able to undo registering for an event. | 13 | 30 | 2
35 | Should | Admin | The admin should be able to delete events citizens have posted. | 2022-11-01 | 30 | 1
36 | Should | Admin | The admin should be able to add tags to posts. | 10 | 20 | 3
37 | Should | Citizen | The citizen should be able to view posts in a tag they are interested in. | 36 | 20 | 3
38 | Should | System | The system should dynamically update events and close polls once the time has expired. | 2 | 20 | 4
39 | Should | Citizen | The citizen should be logged out after a certain amount of time inactive to ensure that the account doesn't get compromised. | 3 | 20 | 2
40 | Could | Citizen | The citizen could search the website for events using keywords. | 36 37 | 50 | 1
41 | Could | Citizen | The citizen could see the top discussions for the current month on the main page. | 13 | 40 | 4
42 | Could | Citizen | The citizen could see the top events for the current month on the main page. | 13 | 30 | 2
43 | Could | System | The system could have a "dark mode" colour scheme (high contrast). (PIPEDA) | 5 | 50 | 1
44 | Could | Citizen | The citizen could be able to sign up for event notifications. | NA | 50 | 1
45 | Could | Citizen | The citizen could be able to contact an event coordinator. | NA | 50 | 2
46 | Could | Citizen | The citizen could be able to see a list of municipality leaders. | NA | 40 | 2
47 | Could | Admin | The system could notify admins about inappropriate post flags. | 1 24 31 | 40 | 3
48 | Could | Citizen | The citizen could "Like" comments from other citizens. | 13 22 23 | 20 | 1
49 | Could | Admin | The citizen could report other citizens’ comments in case they are misleading or irrelevant to the topic. | 23 31 | 40 | 3
50 | Could | Admin | The admin could access citizen data without directly interacting with the system's UI. | 32 | 30 | 3
51 | Could | Citizen | The admin could be able to approve comments on posts. | 22 47 49 | 40 | 2
52 | Could | System | The system could supply a .ics file that lets citizen add event to calendar. | 2022-10-09 | 40 | 3
53 | Could | Citizen | The citizen could add the event to their calendar. | 52 | 40 | 3
54 | Wont | Citizen | The citizen won't require authentication to access the site. | NA | NA | NA
55 | Wont | Admin | The admins won't be able to communicate with each other on the site. | NA | NA | NA
56 | Wont | System | The system won't give citizens from outside the city access to city feedback. | NA | NA | NA
57 | Wont | Citizen | The citizen won't be permitted to be collecting emails or other client data. | NA | NA | NA
58 | Wont | System | The system won't reveal emails, names or any personal information in event postings/polls. | NA | NA | NA